## Compliance Matrix
RFP Compliance Matrix
Track Section L requirements against proposal response sections
Compliance Summary
Compliant | 11
Partial | 6
Non-Compliant | 2
N/A | 1
Total Requirements | 20
L-001 | L.5.1.1 | Cover Letter — Signed by authorized corporate official; identify offeror, CAGE code, DUNS, address, and POC | I — Admin | Vol I, Section 1.0 | Compliant | Cover letter template finalized | Contracts Mgr | 2026-04-20
L-002 | L.5.1.2 | Executive Summary — 5-page maximum; summarize technical approach, relevant experience, and key personnel | I — Admin | Vol I, Section 2.0 | Compliant | Draft complete; final review pending | Capture Lead | 2026-04-18
L-003 | L.5.2.1 | Technical Approach — Describe methodology to meet SOW requirements in Section C; include WBS | II — Tech | Vol II, Section 1.0 | Partial | WBS diagram in progress; narrative 80% complete | Tech Lead | 2026-04-22
L-004 | L.5.2.2 | Systems Engineering Plan — Describe SE processes, tools, and standards (MIL-STD-882E, IEEE 15288) | II — Tech | Vol II, Section 2.0 | Compliant | SE plan aligned with customer standards | Systems Engr | 2026-04-17
L-005 | L.5.2.3 | Transition Plan — 90-day transition-in plan with risk mitigation and knowledge transfer approach | II — Tech | Vol II, Section 3.0 | Non-Compliant | Transition timeline draft incomplete; need sub input | PM | 2026-04-25
L-006 | L.5.2.4 | Cybersecurity Approach — Describe compliance with NIST 800-171 and CMMC Level 2 requirements | II — Tech | Vol II, Section 4.0 | Partial | CMMC gap analysis underway; SSP in development | ISSM | 2026-04-23
L-007 | L.5.2.5 | Quality Assurance Surveillance Plan (QASP) — Describe QA processes and metrics tracking | II — Tech | Vol II, Section 5.0 | Compliant | QASP aligned with PWS performance standards | QA Lead | 2026-04-16
L-008 | L.5.3.1 | Management Approach — Organizational chart, staffing plan, and communication strategy | III — Mgmt | Vol III, Section 1.0 | Compliant | Org chart finalized; staffing plan approved | PM | 2026-04-19
L-009 | L.5.3.2 | Key Personnel — Resumes for PM, Deputy PM, Technical Lead; 5-page max per resume | III — Mgmt | Vol III, Section 2.0 | Partial | PM and Tech Lead resumes ready; Deputy PM TBD | HR/Recruiting | 2026-04-21
L-010 | L.5.3.3 | Subcontract Management Plan — Identify major subs; describe oversight and flow-down requirements | III — Mgmt | Vol III, Section 3.0 | Compliant | Teaming agreements executed; flow-downs mapped | Subcontracts Mgr | 2026-04-18
L-011 | L.5.4.1 | Past Performance — 5 relevant contracts within last 5 years; include CPARS ratings and POC info | IV — PP | Vol IV, Section 1.0 | Compliant | 5 references selected; questionnaires sent | BD Lead | 2026-04-17
L-012 | L.5.4.2 | Past Performance Questionnaires — Submit PPQ to each reference; provide completed forms in proposal | IV — PP | Vol IV, Section 2.0 | Partial | 3 of 5 questionnaires returned; following up on 2 | BD Lead | 2026-04-24
L-013 | L.5.5.1 | Cost/Price Volume — Fully loaded labor rates by LCAT; indirect rate build-up; basis of estimate | V — Cost | Vol V, Section 1.0 | Compliant | Rate build-up complete; DCAA-auditable format | Finance Dir | 2026-04-20
L-014 | L.5.5.2 | Subcontractor Pricing — Include sub cost proposals; adequate price competition or cost analysis | V — Cost | Vol V, Section 2.0 | Non-Compliant | Awaiting 2 sub cost proposals; deadline approaching | Subcontracts Mgr | 2026-04-27
L-015 | L.5.6.1 | CDRL Deliverables List — Acknowledge all CDRLs in DD Form 1423; provide delivery schedule | II — Tech | Vol II, Appendix A | Compliant | All 23 CDRLs mapped and acknowledged | Tech Writer | 2026-04-16
L-016 | L.5.6.2 | DD Form 254 — Security Classification Guide acknowledgment; personnel clearance plan | I — Admin | Vol I, Section 3.0 | Compliant | DD 254 reviewed; FSO coordination complete | FSO | 2026-04-17
L-017 | L.5.7.1 | Small Business Subcontracting Plan — Meet or exceed SB goals per FAR 19.704; include ISR/SSR commitment | I — Admin | Vol I, Section 4.0 | Partial | SB plan at 35% vs 38% target; identifying additional SBs | SB Liaison | 2026-04-22
L-018 | L.5.7.2 | Organizational Conflict of Interest (OCI) — Mitigation plan per FAR 9.5; disclose potential conflicts | I — Admin | Vol I, Section 5.0 | N/A | No OCIs identified; self-certification letter prepared | Legal | 2026-04-16
L-019 | L.5.8.1 | Section 508 Compliance — Describe approach to accessible deliverables per Section 508 of Rehab Act | II — Tech | Vol II, Section 6.0 | Compliant | 508 compliance plan based on WCAG 2.1 AA | IT Lead | 2026-04-18
L-020 | L.5.8.2 | Phase-In/Phase-Out Plan — Describe contractor demobilization and data/IP transfer at contract end | II — Tech | Vol II, Section 7.0 | Partial | Phase-out plan outline drafted; detail needed on IP transfer | PM | 2026-04-23
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com
Generated: 2026-03-23

## Instructions
RFP Compliance Matrix — Instructions
Purpose
This compliance matrix ensures your proposal response addresses every requirement in the RFP's Section L (Instructions to Offerors). It maps each requirement to your proposal volume, section, and current compliance status. A complete, accurate compliance matrix is the single most important tool for avoiding non-compliance findings during evaluation.
Column Definitions
Req #: A unique identifier for tracking each requirement (e.g., L-001, L-002). Use a consistent numbering scheme that maps to the RFP section structure.
Section L Reference: The specific paragraph or section number from the RFP's Section L where this requirement appears (e.g., L.5.2.1).
Requirement Summary: A concise restatement of the requirement in your own words. Include page limits, format restrictions, and key deliverables specified.
Volume: The proposal volume where this requirement will be addressed (e.g., Volume I — Administrative, Volume II — Technical, Volume III — Management, Volume IV — Past Performance, Volume V — Cost/Price).
Page/Section in Proposal: The exact section and page reference in your proposal where this requirement is addressed. Update as the proposal develops.
Response Status: Current compliance status: Compliant (fully addresses the requirement), Partial (partially addresses; gaps remain), Non-Compliant (does not yet address the requirement), N/A (not applicable to your offer).
Compliance Note: Brief explanation of your compliance approach or identification of gaps. For Partial/Non-Compliant items, describe what is needed to achieve compliance.
Owner: The individual responsible for drafting or completing the response to this requirement.
Due Date: The internal deadline for completing the response to this requirement. Set dates well before the proposal submission deadline.
Tips for Avoiding Non-Compliance
1. Start Early: Begin the compliance matrix as soon as the RFP is released. Do not wait for the proposal outline to be complete.
2. Read Section M: Cross-reference Section M (Evaluation Criteria) with Section L. Evaluators score based on M; your proposal must respond to L in a way that maximizes M scores.
3. Use Shredding: Perform a detailed 'RFP shred' — break every sentence in Section L into individual requirements. A single paragraph may contain 3-5 discrete requirements.
4. Track Amendments: Update the matrix whenever an RFP amendment is issued. Amendments frequently change requirements, page limits, or evaluation criteria.
5. Color Review: Conduct color reviews (Pink/Red/Gold) using this matrix as the checklist. Every row should be 'Compliant' before Gold review.
6. Cross-Reference CDRLs: Ensure all Contract Data Requirements List (CDRL) items in Section J are addressed in your technical volume.
7. Compliance = Responsiveness: A non-compliant proposal may be rated 'unacceptable' and eliminated from competition regardless of technical merit. Compliance is non-negotiable.
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com