## EVM Quick Reference
EVM Formulas Quick Reference |  |  |  |  | ACQLERATE
Earned Value Management — Defense Acquisitions Academy |  |  |  |  | Pin to your wall!
1. THE THREE FUNDAMENTAL VALUES
Metric |  | Plain English |  |  | Also Known As
PV (Planned Value) |  | The budgeted cost for work scheduled to be done by now |  |  | BCWS — Budgeted Cost of Work Scheduled
EV (Earned Value) |  | The budgeted cost for work actually completed so far |  |  | BCWP — Budgeted Cost of Work Performed
AC (Actual Cost) |  | The actual cost incurred for work completed so far |  |  | ACWP — Actual Cost of Work Performed
2. VARIANCE METRICS
Metric |  | Formula |  | Positive = Good |  | Negative = Bad
CV (Cost Variance) |  | EV − AC |  | Under budget |  | Over budget
SV (Schedule Variance) |  | EV − PV |  | Ahead of schedule |  | Behind schedule
VAC (Variance at Completion) |  | BAC − EAC |  | Expected underrun |  | Expected overrun
3. PERFORMANCE INDEX METRICS
Index |  | Formula |  | > 1.0 |  | < 1.0
CPI (Cost Performance Index) |  | EV / AC |  | Under budget — efficient |  | Over budget — burning cash
SPI (Schedule Perf. Index) |  | EV / PV |  | Ahead of schedule |  | Behind schedule
TCPI (To-Complete Perf. Index) |  | (BAC−EV) / (BAC−AC) |  | Lower = easier path forward |  | Higher = harder to recover
★ Rule of Thumb: After 20% completion, CPI rarely improves by more than 10%. Plan accordingly — history shows overruns persist.
4. ESTIMATE AT COMPLETION (EAC) — Four Methods
Method | Formula |  | When to Use |  |  | Accuracy
#1 — CPI-Based | BAC / CPI |  | Most common. Assumes future cost efficiency = past. Most accurate after 20% complete. |  |  | ★★★★
#2 — Optimistic | AC + (BAC − EV) |  | Assumes overrun is non-recurring (one-time issue). Use with caution. |  |  | ★★
#3 — PM Estimate | AC + ETC (new est.) |  | PM provides fresh bottom-up estimate of remaining work. Use for major re-plans. |  |  | ★★★
#4 — Pessimistic | AC + (BAC−EV)/(CPI×SPI) |  | Accounts for BOTH cost and schedule inefficiency. Worst-case realism. |  |  | ★★★★
5. QUICK INTERPRETATION GUIDE — CPI / SPI Ranges
Range |  | Status |  | What It Means |  | Action Required
≥ 1.00 |  | GREEN |  | On or under budget/schedule |  | Continue monitoring
0.90 – 0.99 |  | AMBER |  | Slightly over budget/behind schedule |  | Investigate root cause; corrective action plan
0.80 – 0.89 |  | RED |  | Significant cost/schedule overrun |  | Formal CAP required; OTB/OTS consideration
< 0.80 |  | CRITICAL |  | Severe — likely unrecoverable without re-baseline |  | EAC revision; Nunn-McCurdy breach possible (>15%)
6. CONTRACT PERFORMANCE REPORT (CPR) FORMATS
Format |  | Description
Format 1 — WBS |  | Work Breakdown Structure — cost/schedule data by WBS element (product-oriented)
Format 2 — Org |  | Organizational — cost/schedule data by performing organization (functional view)
Format 3 — Baseline |  | Baseline — time-phased PMB showing budget distribution over time
Format 4 — Staffing |  | Staffing — labor hours (actual & forecast) by month, by functional category
Format 5 — Narrative |  | Explanations & Variance Analysis — written analysis of significant variances
7. KEY EVM TERMS
PMB | Performance Measurement Baseline — the time-phased budget plan against which performance is measured |  |  | BAC | Budget At Completion — total budget for the authorized work (PMB total)
CBB | Contract Budget Base — negotiated contract cost + authorized unpriced work |  |  | MR | Management Reserve — budget held by PM for unknown unknowns; NOT in PMB
UB | Undistributed Budget — budget allocated to the contract but not yet assigned to WBS elements |  |  | WBS | Work Breakdown Structure — product-oriented hierarchy decomposing project scope
CAP | Control Account Plan — the management control point where scope, schedule, budget intersect |  |  | OTB/OTS | Over Target Baseline/Schedule — formal re-baselining when PMB is no longer achievable
© 2026 Acqlerate — Defense Acquisitions Academy ¦ acqlerate.com ¦ Reference: ANSI/EIA-748, DoDI 5000.02, OMB Circular A-11