## Risk Register
DoD Program Risk Register
Track, assess, and mitigate program risks per DoD Risk Management Framework
Risk Summary
By Risk Level |  |  | By Category |  |  | By Status
HIGH |  |  | Technical |  |  | Open
MEDIUM |  |  | Schedule |  |  | Mitigated
LOW |  |  | Cost |  |  | Closed
|  |  | External |  |  | Accepted
Programmatic
R-001 | Software Integration Failure | Technical | Integration of legacy C4ISR systems with new cloud-based architecture may fail due to incompatible interfaces and undocumented APIs | 4 | 5 |  | Conduct early integration testing in sprint 2; establish interface control documents (ICDs) before CDR | Revert to point-to-point integration with middleware adapter layer | Systems Engineer | 2026-04-22 | Open | 2026-03-23
R-002 | Key Personnel Departure | Programmatic | Program Manager or Technical Lead may depart during performance period, causing knowledge loss and schedule delays | 3 | 4 |  | Cross-train deputy PM; maintain knowledge repository; include retention incentives in compensation plan | Activate pre-identified replacement from bench; execute 30-day transition plan | HR Director | 2026-05-22 | Open | 2026-03-23
R-003 | Requirements Creep | Schedule | Government may issue numerous contract modifications expanding scope without proportional schedule/cost adjustments | 4 | 4 |  | Establish formal change control board; track all requirements changes against baseline; negotiate equitable adjustments promptly | Invoke REA process; request stop-work on unfunded requirements until modification is executed | PM | 2026-05-07 | Open | 2026-03-23
R-004 | Funding Shortfall / CR Impact | Cost | Continuing Resolution or sequestration may reduce available program funding below planned obligation levels | 3 | 5 |  | Maintain prioritized requirements backlog; identify minimum viable capability set; coordinate with PEO on funding alternatives | Descope optional CLINs; defer non-critical deliverables to subsequent option years | Finance Director | 2026-06-21 | Open | 2026-03-23
R-005 | Subcontractor Performance | External | Critical subcontractor (cybersecurity toolset provider) may fail to deliver on schedule or meet quality standards | 3 | 4 |  | Conduct monthly sub performance reviews; include liquidated damages clause; maintain qualified alternate vendor list | Activate alternate vendor under pre-negotiated teaming agreement; absorb initial ramp-up costs | Subcontracts Mgr | 2026-04-22 | Open | 2026-03-23
R-006 | CMMC Certification Delay | External | CMMC Phase 1 (self-assessment, Level 2) is active as of Nov 10, 2025. Phase 2 requires a C3PAO third-party assessment, mandatory by Nov 10, 2026. Organization must complete C3PAO assessment before Phase 2 deadline to remain eligible for DoD contracts involving CUI. | 2 | 5 |  | Complete CMMC Level 2 self-assessment (Phase 1) immediately; remediate any POA&M gaps. Engage accredited C3PAO assessor NLT Q1 2026 to schedule Phase 2 assessment before the Nov 10, 2026 mandatory deadline. Track via CMMC AB Marketplace. | If C3PAO assessment cannot be completed before Nov 10, 2026, consult CO on contract impact and explore interim authorization options; ensure SPRS score reflects current NIST 800-171 implementation posture. | ISSM | 2026-07-21 | Mitigated | 2026-03-23
R-007 | Test Environment Unavailability | Technical | Government-furnished test range or lab environment may not be available during scheduled test windows | 3 | 3 |  | Reserve test windows 90 days in advance; develop simulation environment for initial testing; coordinate with range scheduling office | Use contractor lab environment with government-approved test procedures; reschedule to next available window | Test Director | 2026-05-07 | Open | 2026-03-23
R-008 | Data Rights Dispute | Programmatic | Disagreement with government over technical data rights (DFARS 252.227-7013) may delay deliverable acceptance | 2 | 4 |  | Document all data rights assertions in proposal; maintain IP development records; engage legal counsel early | Negotiate limited rights license; escalate to CO for determination; consider ASBCA claim if unresolved | Legal Counsel | 2026-05-22 | Accepted | 2026-03-23
R-009 | EVM Compliance Gaps | Cost | Earned Value Management System may not meet ANSI/EIA-748 standards, resulting in DCMA surveillance findings | 2 | 3 |  | Conduct EVMS self-assessment; train all CAMs on EVM procedures; schedule pre-IBR dry run | Engage EVM consultant for remediation; request corrective action timeline extension from DCMA | Finance Director | 2026-04-22 | Mitigated | 2026-03-23
R-010 | Supply Chain Disruption | External | Critical hardware components (FPGA chips, ruggedized servers) may face extended lead times exceeding 6 months | 4 | 3 |  | Order long-lead items at contract award; qualify multiple vendors; maintain safety stock for critical components | Redesign with available commercial alternatives; negotiate schedule relief through REA | Logistics Mgr | 2026-04-07 | Open | 2026-03-23
R-011 | Clearance Processing Delays | Schedule | Personnel security clearance investigations may exceed expected timelines, delaying staffing of classified positions | 3 | 3 |  | Submit clearance requests immediately upon contract award; utilize interim clearances where permissible; pre-identify cleared alternates | Assign cleared personnel from other programs temporarily; adjust task sequencing to prioritize unclassified work | FSO | 2026-04-22 | Open | 2026-03-23
R-012 | Technical Debt Accumulation | Technical | Aggressive delivery schedule may force shortcuts in code quality, increasing defect rates and long-term maintenance costs | 3 | 3 |  | Allocate 20% sprint capacity for refactoring; enforce code review gates; track technical debt backlog | Dedicate full sprint to debt reduction when defect rate exceeds threshold; engage additional developers | Tech Lead | 2026-05-22 | Open | 2026-03-23
R-013 | Government Stakeholder Turnover | Programmatic | COR or program office key personnel may rotate, requiring re-education and potentially changing program priorities | 3 | 2 |  | Maintain comprehensive program documentation; build relationships across the program office; brief incoming personnel proactively | Request transition meeting with outgoing/incoming COR; provide program status briefing package | PM | 2026-06-21 | Accepted | 2026-03-23
R-014 | Protest Delays Contract Start | Schedule | Losing offeror may file GAO protest, delaying contract award by 60-100 days and compressing performance schedule | 2 | 4 |  | Build schedule float into early milestones; prepare mobilization plan executable on short notice; maintain team availability during protest | Compress initial transition period; request schedule adjustment through contract modification | PM | 2026-04-07 | Open | 2026-03-23
R-015 | Nunn-McCurdy Breach Risk | Cost | Program cost growth may approach Nunn-McCurdy unit cost thresholds, triggering Congressional notification and potential cancellation review | 1 | 5 |  | Monitor unit cost trends monthly against APB thresholds; report cost variances exceeding 5% immediately to PEO | Prepare program restructure brief; identify cost reduction opportunities; coordinate with CAPE for independent cost estimate | Finance Director | 2026-06-21 | Open | 2026-03-23
R-016 | CMMC Level 2 Non-Compliance | External | Subcontractors handling Controlled Unclassified Information (CUI) may not complete required C3PAO third-party assessment before CMMC Phase 2 takes effect Nov 10, 2026, risking their eligibility to remain on contract | 3 | 5 |  | Confirm CMMC Level 2 self-assessment status for every subcontractor handling CUI now; require proof of scheduled C3PAO assessment; fund the assessment cost through a subcontract modification if needed | Pre-qualify an alternate subcontractor already holding current CMMC Level 2 certification; be ready to transition CUI-handling work on short notice | Subcontracts Mgr | 2026-10-01 | Open | 2026-09-01
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com

## Risk Matrix Chart
5×5 Probability / Impact Risk Matrix
Risk Score = Probability × Impact ¦ GREEN ≤7 (LOW) ¦ YELLOW 8-14 (MEDIUM) ¦ RED ≥15 (HIGH)
Probability ↓ / Impact → | 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Significant | 5 — Critical
5 — Almost Certain | 5 | 10 | 15 | 20 | 25
4 — Likely | 4 | 8 | 12 | 16 | 20
3 — Possible | 3 | 6 | 9 | 12 | 15
2 — Unlikely | 2 | 4 | 6 | 8 | 10
1 — Rare | 1 | 2 | 3 | 4 | 5
Legend
HIGH (≥15) | Unacceptable risk — requires immediate mitigation action and leadership attention
MEDIUM (8-14) | Elevated risk — requires active monitoring and mitigation planning
LOW (≤7) | Acceptable risk — monitor periodically; no immediate action required
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com
Where Your Risks Land
Pulls live from the Risk Register. Print this page and drop it straight into your weekly program review slide.
Probability ↓ / Impact → | 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Significant | 5 — Critical
5 — Almost Certain
4 — Likely
3 — Possible
2 — Unlikely
1 — Rare
Blank cell = no risk currently scored at that Probability × Impact combination.
License & Use
This template is licensed for use on one program, by one organization, under your Acqlerate purchase. Customize the text, branding, and layout freely for your own program. Deploying it company-wide, sharing it outside your organization, or reselling it requires an Acqlerate Team License (acqlerate.com/team).