## RACI Matrix
RACI Matrix — DoD Program Stakeholders (Simplified)
One row per activity. List the Responsible and Accountable role, plus anyone to Consult or Inform.
Legend: R = Responsible (does the work) ¦ A = Accountable (owns the outcome, one per row)
C = Consulted (input before the decision) ¦ I = Informed (notified after)
Activity / Decision | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I)
Program Initiation | PM | PEO | CO, Systems Engineer, Finance, Legal | COR, DCMA, Contractor PM
Requirements Development | PM, Systems Engineer | PEO | COR, Contractor PM | CO, DCMA, Finance, Legal
Acquisition Strategy | PM | PEO | CO, DCAA, Systems Engineer, Finance, Legal | COR, DCMA, Contractor PM
Source Selection Planning | CO | PEO | PM, COR, Systems Engineer, Legal | DCMA, Contractor PM, Finance
RFP Development & Release | CO | PEO | PM, COR, Systems Engineer, Legal | Finance
Proposal Evaluation | PM, Systems Engineer | CO | COR, Finance, Legal | PEO
Contract Award | CO | PEO | Finance, Legal | PM, COR, DCMA, Contractor PM
Kickoff Meeting | PM, COR, Contractor PM | PM | CO, Systems Engineer | PEO, DCMA, Finance
Monthly IPR / Status Review | PM, Contractor PM | COR | Systems Engineer, Finance | PEO, CO, DCMA
Quarterly Program Review | PM, Contractor PM | PEO | COR, DCMA, Systems Engineer, Finance | CO
EVM / CPR Review | PM, Contractor PM, Finance | PM | COR, DCMA, DCAA | PEO, CO
CDR / PDR Review | PM, Contractor PM, Systems Engineer | PEO | COR, DCMA | CO, Finance
Test Planning | Contractor PM, Systems Engineer | PM | COR, DCMA | PEO, CO, Finance
Test Execution | COR, Contractor PM, Systems Engineer | PM | DCMA | PEO, CO, Finance
Deliverable Acceptance | COR, Contractor PM | PM | DCMA, Systems Engineer | PEO, CO, Finance
Invoice Review & Approval | COR, Contractor PM, Finance | CO | DCMA, DCAA | PM, PEO
Contract Modification | PM, CO | PEO | COR, Contractor PM, Systems Engineer, Finance, Legal | DCMA, DCAA
Risk Review Board | PM, Contractor PM | PM | COR, Systems Engineer, Finance | PEO, CO, DCMA
COR Surveillance | COR | CO | DCMA | PM, PEO, Contractor PM
CPARS Rating | COR | CO | PM, DCMA | PEO, Contractor PM
Nunn-McCurdy Reporting | PM, Finance | PEO | Contractor PM, Systems Engineer, Legal | CO, COR, DCMA
APB Baseline Update | PM, Finance | PEO | Contractor PM, Systems Engineer | CO, COR, DCMA
Milestone Decision Review | PM, Systems Engineer | PEO | CO, DCMA, Contractor PM, Finance, Legal | COR
Contract Close-Out | CO, COR, Contractor PM, Finance | PM | DCMA, DCAA, Legal | PEO
Lessons Learned / AAR | PM, Contractor PM | PM | COR, Systems Engineer | PEO, CO, DCMA, Finance
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com
Generated: September 2026 ¦ Updated: FAC 2025-06

## Instructions
RACI Matrix — Instructions
Purpose
The RACI matrix clarifies who does the work, who owns the outcome, who gets consulted, and who just needs to know. It prevents the "I thought you were handling that" problem on DoD programs.
Why this version is a list, not a grid
The classic RACI matrix (one column per stakeholder role) is thorough but nobody keeps it updated: adding a new activity means filling in ten columns. This version flips it: one row per activity, with just four fields. Adding or editing an activity takes seconds.
RACI Definitions
R — Responsible: The person or role that performs the work. More than one person can be Responsible.
A — Accountable: The single person with final authority for the outcome. Exactly one per activity, no exceptions.
C — Consulted: People whose input is sought before the decision or action (two-way conversation).
I — Informed: People notified after the decision or action (one-way notice).
Stakeholder Roles Used in This Template
PM: Government Program Manager — overall program execution authority, accountable to the PEO for cost, schedule, and performance.
PEO: Program Executive Officer — senior acquisition authority; provides oversight and milestone approval.
CO: Contracting Officer — legal authority to obligate funds and award or modify contracts.
COR: Contracting Officer's Representative — the CO's eyes and ears on the program; monitors contractor performance.
DCMA: Defense Contract Management Agency — contract administration and EVMS surveillance.
DCAA: Defense Contract Audit Agency — audits contractor accounting systems and incurred costs.
Contractor PM: The contractor's Program Manager — leads the contractor team executing the work.
Systems Engineer: Technical authority for design, integration, and requirements.
Finance: Manages budget execution, obligations, and financial reporting.
Legal: Legal counsel on contract matters, protests, disputes, and IP.
How to Customize
1. To edit an activity: just retype the Responsible, Accountable, Consulted, or Informed cell. No other cell has to change.
2. To add an activity: add a new row with the activity name and its four fields. There is no matrix to extend.
3. To remove an activity: delete the row.
4. Every row must have exactly one Accountable owner. If a cell is blank, decide who owns it before you ship the RACI.
5. Consulted and Informed can list more than one name, separated by commas.
6. Brief this RACI at kickoff and store it with the Program Management Plan. Update it whenever a role changes hands.
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com
License & Use
This template is licensed for use on one program, by one organization, under your Acqlerate purchase. Customize the text, branding, and layout freely for your own program. Deploying it company-wide, sharing it outside your organization, or reselling it requires an Acqlerate Team License (acqlerate.com/team).