## Slide 1
[Program Name]
Program Status Review
[Month Year]
UNCLASSIFIED // FOUO
Acqlerate — Defense Acquisitions Academy
Notes: WHAT LEADERSHIP WILL ASK
They will ask: What changed since last time? Have a one-sentence answer ready before the title slide is off the screen.
IF THIS SLIDE IS RED (or you are asked to defend it)
Say the classification level out loud. Confirm the audience and the decision you need from them today, if any.

## Slide 2
Agenda
01
Executive Summary
Overall program health and key highlights
02
Program Status
Milestone progress and current activities
03
Schedule Status
IMS performance, SPI metrics, critical path
04
Cost / EVM Status
CPI, SPI, EAC, VAC, and cost trends
05
Risk Status
Top risks, mitigation progress, new risks
06
Way Forward
30/60/90-day plan and decision requests
[Program Name] | Program Status Review | [Month Year]
2
Notes: WHAT LEADERSHIP WILL ASK
They will ask: How long is this? What do you need from me?
IF THIS SLIDE IS RED (or you are asked to defend it)
State the ask up front: information only, or a decision. If a decision, name it here so nobody is surprised on slide 11.

## Slide 3
Executive Summary
Program Health
Cost
Schedule
Performance
Key Accomplishments
Completed PDR with no major action items
Software Build 3.1 delivered on schedule
All CDRLs current; no delinquencies
Subcontractor performance meeting all KPIs
Top Issues
Key personnel vacancy: Deputy PM position unfilled since Feb
Schedule pressure on Integration Test milestone (15 Apr)
Awaiting CO decision on Mod 04 (scope addition)
[Program Name] | Program Status Review | [Month Year]
3
Notes: WHAT LEADERSHIP WILL ASK
They will ask: Why is that light red? What are you doing about it? When will it be green?
IF THIS SLIDE IS RED (or you are asked to defend it)
If red: one sentence on cause, one on the fix, one on the date. Never explain a red for more than 30 seconds on this slide; the detail is later.

## Slide 4
Program Status
The program is currently in the Engineering & Manufacturing Development (EMD) phase. CDR is complete and the team is executing integration and test activities. No Nunn-McCurdy breaches or APB threshold exceedances.
Milestone | Baseline Date | Forecast Date | Status
PDR Complete | 15 Oct 2025 | 15 Oct 2025 | COMPLETE
CDR Complete | 15 Jan 2026 | 20 Jan 2026 | COMPLETE
Integration Test Start | 01 Apr 2026 | 15 Apr 2026 | AT RISK
System Test Complete | 15 Jul 2026 | 15 Jul 2026 | ON TRACK
IOT&E Start | 01 Oct 2026 | 01 Oct 2026 | ON TRACK
IOC Declaration | 15 Jan 2027 | 15 Jan 2027 | ON TRACK
FOC Declaration | 01 Jul 2027 | 01 Jul 2027 | PLANNED
[Program Name] | Program Status Review | [Month Year]
4
Notes: WHAT LEADERSHIP WILL ASK
They will ask: Are we on the baseline? What is the biggest thing that could take us off it?
IF THIS SLIDE IS RED (or you are asked to defend it)
Name your top risk here even though the risk slide is later. Leadership remembers what you led with.

## Slide 5
Schedule Status
SPI
0.96
Slightly Behind
IMS Summary
Total IMS Activities: 847 | Complete: 612 (72%) | In Progress: 89 | Not Started: 146
Critical path runs through Integration Test activities. A 14-day slip in CDR close-out has compressed the integration test schedule. Recovery plan focuses on parallel test execution and weekend staffing for the test team.
Near-Term Milestone | Baseline | Forecast | Variance | Critical Path?
Integration Test Readiness Review | 25 Mar 2026 | 08 Apr 2026 | +14 days | Yes
Integration Test Start | 01 Apr 2026 | 15 Apr 2026 | +14 days | Yes
Software Build 3.2 Delivery | 10 Apr 2026 | 10 Apr 2026 | 0 days | No
Interface Control Document Update | 20 Apr 2026 | 20 Apr 2026 | 0 days | No
Integration Test Complete | 30 Jun 2026 | 30 Jun 2026 | TBD | Yes
[Program Name] | Program Status Review | [Month Year]
5
Notes: WHAT LEADERSHIP WILL ASK
They will ask: What is on the critical path? How much float do we have? What slipped and why?
IF THIS SLIDE IS RED (or you are asked to defend it)
If SPI is below 0.95: say what task drove it and whether it recovers or is permanent. 'The contractor is working it' is not an answer.

## Slide 6
Cost / EVM Status
CPI
1.02
On Budget
SPI
0.96
Slightly Behind
EAC
$47.2M
vs BAC $48.0M
VAC
+$0.8M
Favorable
EVM Element | BCWS | BCWP | ACWP | SV | CV
Cumulative ($M) | $24.5 | $23.5 | $23.0 | ($1.0) | $0.5
Current Month ($M) | $2.1 | $2.0 | $1.95 | ($0.1) | $0.05
Trend: CPI has been stable above 1.0 for 6 consecutive months. SPI dipped below 1.0 this month due to CDR close-out delay; recovery expected by April.
[Program Name] | Program Status Review | [Month Year]
6
Notes: WHAT LEADERSHIP WILL ASK
They will ask: What is the EAC? Do you believe it? How much management reserve is left?
IF THIS SLIDE IS RED (or you are asked to defend it)
If CPI is below 0.95: state your independent EAC, not just the contractor's. If they differ by more than 5%, say why.

## Slide 7
Risk Status
3 HIGH | 5 MEDIUM | 4 LOW | Total: 12 Open Risks
Risk | P | I | Score | Level | Mitigation Status
Integration test schedule compression | 4 | 5 | 20 | HIGH | Parallel test plan approved; weekend staffing authorized
Key personnel vacancy (Deputy PM) | 3 | 4 | 12 | MED | Recruiting in progress; 3 candidates in pipeline
Subcontractor deliverable quality | 3 | 4 | 12 | MED | Weekly quality reviews implemented; CAR issued
Funding uncertainty (FY27 POM) | 3 | 5 | 15 | HIGH | POM submission complete; PEO advocacy scheduled
CMMC Level 2 assessment timeline | 2 | 5 | 10 | MED | C3PAO engagement initiated; target Aug 2026
New risk this period: CMMC assessment timeline added based on C3PAO scheduling constraints. Closed risk: Software license expiration (renewed through FY27).
[Program Name] | Program Status Review | [Month Year]
7
Notes: WHAT LEADERSHIP WILL ASK
They will ask: What is new? What got worse? Who owns the red ones?
IF THIS SLIDE IS RED (or you are asked to defend it)
Show the Risk Map from the workbook. Every HIGH risk needs an owner by name and a mitigation with a date. If you cannot name the owner, that is the finding.

## Slide 8
Technical Progress
Accomplishments This Period
Completed CDR close-out with 3 minor RFAs resolved
Software Build 3.1 passed all unit tests (98.7% code coverage)
Interface Control Documents updated for 4 external systems
Cybersecurity RMF Assessment package submitted to SCA
Delivered 3 CDRLs on schedule (SDD, IDD, STP)
Planned Next Period
Begin Integration Test execution (target 15 Apr)
Complete Software Build 3.2 development and unit testing
Conduct ITRR (Integration Test Readiness Review)
Finalize system test procedures with IV&V team
Submit RMF ATO package to AO
[Program Name] | Program Status Review | [Month Year]
8
Notes: WHAT LEADERSHIP WILL ASK
They will ask: Are requirements stable? What is the next design review and are we ready?
IF THIS SLIDE IS RED (or you are asked to defend it)
If a technical review slipped: was it the contractor, the government, or requirements? Say which. It changes the fix.

## Slide 9
Contractor Performance Assessment
CPARS-aligned assessment for current evaluation period
Assessment Area | Rating | Trend | Comments
Technical Quality | Satisfactory | Stable | Deliverables meet requirements; CDR completed with minor findings only
Schedule | Marginal | Declining | 14-day slip on CDR close-out; recovery plan submitted
Cost Control | Satisfactory | Improving | CPI > 1.0 for 6 consecutive months; good cost discipline
Management | Satisfactory | Stable | Responsive to government direction; proactive risk management
Staffing | Marginal | Declining | Deputy PM vacancy persists; recruitment efforts underway
Regulatory Compliance | Satisfactory | Stable | All regulatory requirements met; CMMC prep on track
Small Business | Satisfactory | Stable | Meeting SB goals; ISR/SSR submitted on time
[Program Name] | Program Status Review | [Month Year]
9
Notes: WHAT LEADERSHIP WILL ASK
They will ask: Would you give them this CPARS rating today? Any CARs open?
IF THIS SLIDE IS RED (or you are asked to defend it)
Tie every rating to evidence from this period. If you are heading toward a Marginal, leadership should hear it here, not at the annual rating.

## Slide 10
Issues & Action Items
# | Issue / Action Item | Owner | Due Date | Status
AI-001 | Fill Deputy PM vacancy — present candidates to PM for selection | Contractor PM | 15 Apr 2026 | OPEN
AI-002 | Submit Integration Test recovery plan with revised schedule | Contractor PM | 28 Mar 2026 | OPEN
AI-003 | Process Contract Mod 04 for FY26 scope addition | CO | 30 Apr 2026 | IN PROGRESS
AI-004 | Complete DCAA incurred cost audit response | Finance Dir | 15 Apr 2026 | IN PROGRESS
AI-005 | Schedule C3PAO CMMC Level 2 assessment | ISSM | 30 Apr 2026 | OPEN
AI-006 | Update EVM baseline for approved Mod 03 changes | Finance Dir | 31 Mar 2026 | CLOSED
AI-007 | Deliver updated System Test Plan (CDRL A005) | Systems Engr | 10 Apr 2026 | OPEN
[Program Name] | Program Status Review | [Month Year]
10
Notes: WHAT LEADERSHIP WILL ASK
They will ask: What is overdue? What do you need from us to close it?
IF THIS SLIDE IS RED (or you are asked to defend it)
Any action older than 60 days gets explained or closed. Ask for help on this slide; that is what it is for.

## Slide 11
Way Forward
Next 30 Days
Conduct ITRR and begin Integration Testing
Fill Deputy PM vacancy
Deliver Software Build 3.2
Process Mod 04 for FY26 scope
Submit monthly CPR and IPR package
Next 60 Days
Complete Integration Test Phase 1
Finalize System Test procedures
Submit RMF ATO package
Conduct Quarterly Program Review
Update IGCE for Option Year 2
Next 90 Days
Complete all Integration Testing
Begin System Test execution
Achieve CMMC Level 2 readiness
Prepare IOT&E entrance criteria brief
Submit FY27 funding request
Decisions Requested:
1. Approve Integration Test recovery plan (PM) 2. Authorize weekend staffing for test team (PEO) 3. Approve Mod 04 scope and funding (CO)
[Program Name] | Program Status Review | [Month Year]
11
Notes: WHAT LEADERSHIP WILL ASK
They will ask: What decision do you need from me, and by when?
IF THIS SLIDE IS RED (or you are asked to defend it)
If you need a decision, restate it here with the deadline and the cost of delay. If you do not need one, say so and stop.

## Slide 12
Backup / Appendix
Supporting detail, data tables, and additional analysis
UNCLASSIFIED // FOUO
Acqlerate — Defense Acquisitions Academy
Notes: WHAT LEADERSHIP WILL ASK
They will ask: Can I see the detail behind slide X?
IF THIS SLIDE IS RED (or you are asked to defend it)
Keep the spend plan table, the full risk register, and the IMS excerpt here. Do not present them; have them ready.