## Risk Register
DoD Program Risk Register
Track, assess, and mitigate program risks per DoD Risk Management Framework
Risk Summary
By Risk Level |  |  | By Category |  |  | By Status
HIGH |  |  | Technical |  |  | Open
MEDIUM |  |  | Schedule |  |  | Mitigated
LOW |  |  | Cost |  |  | Closed
|  |  | External |  |  | Accepted
Programmatic
R-001 | Software Integration Failure | Technical | Integration of legacy C4ISR systems with new cloud-based architecture may fail due to incompatible interfaces and undocumented APIs | 4 | 5 |  | Conduct early integration testing in sprint 2; establish interface control documents (ICDs) before CDR | Revert to point-to-point integration with middleware adapter layer | Systems Engineer | 2026-04-22 | Open | 2026-03-23
R-002 | Key Personnel Departure | Programmatic | Program Manager or Technical Lead may depart during performance period, causing knowledge loss and schedule delays | 3 | 4 |  | Cross-train deputy PM; maintain knowledge repository; include retention incentives in compensation plan | Activate pre-identified replacement from bench; execute 30-day transition plan | HR Director | 2026-05-22 | Open | 2026-03-23
R-003 | Requirements Creep | Schedule | Government may issue numerous contract modifications expanding scope without proportional schedule/cost adjustments | 4 | 4 |  | Establish formal change control board; track all requirements changes against baseline; negotiate equitable adjustments promptly | Invoke REA process; request stop-work on unfunded requirements until modification is executed | PM | 2026-05-07 | Open | 2026-03-23
R-004 | Funding Shortfall / CR Impact | Cost | Continuing Resolution or sequestration may reduce available program funding below planned obligation levels | 3 | 5 |  | Maintain prioritized requirements backlog; identify minimum viable capability set; coordinate with PEO on funding alternatives | Descope optional CLINs; defer non-critical deliverables to subsequent option years | Finance Director | 2026-06-21 | Open | 2026-03-23
R-005 | Subcontractor Performance | External | Critical subcontractor (cybersecurity toolset provider) may fail to deliver on schedule or meet quality standards | 3 | 4 |  | Conduct monthly sub performance reviews; include liquidated damages clause; maintain qualified alternate vendor list | Activate alternate vendor under pre-negotiated teaming agreement; absorb initial ramp-up costs | Subcontracts Mgr | 2026-04-22 | Open | 2026-03-23
R-006 | CMMC Certification Delay | External | CMMC Phase 1 (self-assessment, Level 2) is active as of Nov 10, 2025. Phase 2 requires a C3PAO third-party assessment, mandatory by Nov 10, 2026. Organization must complete C3PAO assessment before Phase 2 deadline to remain eligible for DoD contracts involving CUI. | 2 | 5 |  | Complete CMMC Level 2 self-assessment (Phase 1) immediately; remediate any POA&M gaps. Engage accredited C3PAO assessor NLT Q1 2026 to schedule Phase 2 assessment before the Nov 10, 2026 mandatory deadline. Track via CMMC AB Marketplace. | If C3PAO assessment cannot be completed before Nov 10, 2026, consult CO on contract impact and explore interim authorization options; ensure SPRS score reflects current NIST 800-171 implementation posture. | ISSM | 2026-07-21 | Mitigated | 2026-03-23
R-007 | Test Environment Unavailability | Technical | Government-furnished test range or lab environment may not be available during scheduled test windows | 3 | 3 |  | Reserve test windows 90 days in advance; develop simulation environment for initial testing; coordinate with range scheduling office | Use contractor lab environment with government-approved test procedures; reschedule to next available window | Test Director | 2026-05-07 | Open | 2026-03-23
R-008 | Data Rights Dispute | Programmatic | Disagreement with government over technical data rights (DFARS 252.227-7013) may delay deliverable acceptance | 2 | 4 |  | Document all data rights assertions in proposal; maintain IP development records; engage legal counsel early | Negotiate limited rights license; escalate to CO for determination; consider ASBCA claim if unresolved | Legal Counsel | 2026-05-22 | Accepted | 2026-03-23
R-009 | EVM Compliance Gaps | Cost | Earned Value Management System may not meet ANSI/EIA-748 standards, resulting in DCMA surveillance findings | 2 | 3 |  | Conduct EVMS self-assessment; train all CAMs on EVM procedures; schedule pre-IBR dry run | Engage EVM consultant for remediation; request corrective action timeline extension from DCMA | Finance Director | 2026-04-22 | Mitigated | 2026-03-23
R-010 | Supply Chain Disruption | External | Critical hardware components (FPGA chips, ruggedized servers) may face extended lead times exceeding 6 months | 4 | 3 |  | Order long-lead items at contract award; qualify multiple vendors; maintain safety stock for critical components | Redesign with available commercial alternatives; negotiate schedule relief through REA | Logistics Mgr | 2026-04-07 | Open | 2026-03-23
R-011 | Clearance Processing Delays | Schedule | Personnel security clearance investigations may exceed expected timelines, delaying staffing of classified positions | 3 | 3 |  | Submit clearance requests immediately upon contract award; utilize interim clearances where permissible; pre-identify cleared alternates | Assign cleared personnel from other programs temporarily; adjust task sequencing to prioritize unclassified work | FSO | 2026-04-22 | Open | 2026-03-23
R-012 | Technical Debt Accumulation | Technical | Aggressive delivery schedule may force shortcuts in code quality, increasing defect rates and long-term maintenance costs | 3 | 3 |  | Allocate 20% sprint capacity for refactoring; enforce code review gates; track technical debt backlog | Dedicate full sprint to debt reduction when defect rate exceeds threshold; engage additional developers | Tech Lead | 2026-05-22 | Open | 2026-03-23
R-013 | Government Stakeholder Turnover | Programmatic | COR or program office key personnel may rotate, requiring re-education and potentially changing program priorities | 3 | 2 |  | Maintain comprehensive program documentation; build relationships across the program office; brief incoming personnel proactively | Request transition meeting with outgoing/incoming COR; provide program status briefing package | PM | 2026-06-21 | Accepted | 2026-03-23
R-014 | Protest Delays Contract Start | Schedule | Losing offeror may file GAO protest, delaying contract award by 60-100 days and compressing performance schedule | 2 | 4 |  | Build schedule float into early milestones; prepare mobilization plan executable on short notice; maintain team availability during protest | Compress initial transition period; request schedule adjustment through contract modification | PM | 2026-04-07 | Open | 2026-03-23
R-015 | Nunn-McCurdy Breach Risk | Cost | Program cost growth may approach Nunn-McCurdy unit cost thresholds, triggering Congressional notification and potential cancellation review | 1 | 5 |  | Monitor unit cost trends monthly against APB thresholds; report cost variances exceeding 5% immediately to PEO | Prepare program restructure brief; identify cost reduction opportunities; coordinate with CAPE for independent cost estimate | Finance Director | 2026-06-21 | Open | 2026-03-23
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com

## Risk Matrix Chart
5×5 Probability / Impact Risk Matrix
Risk Score = Probability × Impact ¦ GREEN ≤7 (LOW) ¦ YELLOW 8-14 (MEDIUM) ¦ RED ≥15 (HIGH)
Probability ↓ / Impact → | 1 — Negligible | 2 — Minor | 3 — Moderate | 4 — Significant | 5 — Critical
5 — Almost Certain | 5 | 10 | 15 | 20 | 25
4 — Likely | 4 | 8 | 12 | 16 | 20
3 — Possible | 3 | 6 | 9 | 12 | 15
2 — Unlikely | 2 | 4 | 6 | 8 | 10
1 — Rare | 1 | 2 | 3 | 4 | 5
Legend
HIGH (≥15) | Unacceptable risk — requires immediate mitigation action and leadership attention
MEDIUM (8-14) | Elevated risk — requires active monitoring and mitigation planning
LOW (≤7) | Acceptable risk — monitor periodically; no immediate action required
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com