## Compliance Matrix
RFP Compliance Matrix
Track Section L requirements against proposal response sections
Compliance Summary
Compliant |  |  | % Complete
Partial
Non-Compliant
N/A
Total Requirements
Status Flag
L-001 | L.5.1.1 | Cover Letter — Signed by authorized corporate official; identify offeror, CAGE code, UEI, address, and POC | I — Admin | Vol I, Section 1.0 | Compliant | Cover letter template finalized | Contracts Mgr | 2026-04-20
L-002 | L.5.1.2 | Executive Summary — 5-page maximum; summarize technical approach, relevant experience, and key personnel | I — Admin | Vol I, Section 2.0 | Compliant | Draft complete; final review pending | Capture Lead | 2026-04-18
L-003 | L.5.2.1 | Technical Approach — Describe methodology to meet SOW requirements in Section C; include WBS | II — Tech | Vol II, Section 1.0 | Partial | WBS diagram in progress; narrative 80% complete | Tech Lead | 2026-04-22
L-004 | L.5.2.2 | Systems Engineering Plan — Describe SE processes, tools, and standards (MIL-STD-882E, IEEE 15288) | II — Tech | Vol II, Section 2.0 | Compliant | SE plan aligned with customer standards | Systems Engr | 2026-04-17
L-005 | L.5.2.3 | Transition Plan — 90-day transition-in plan with risk mitigation and knowledge transfer approach | II — Tech | Vol II, Section 3.0 | Non-Compliant | Transition timeline draft incomplete; need sub input | PM | 2026-04-25
L-006 | L.5.2.4 | Cybersecurity Approach — Describe compliance with NIST 800-171 and CMMC Level 2 requirements | II — Tech | Vol II, Section 4.0 | Partial | CMMC gap analysis underway; SSP in development | ISSM | 2026-04-23
L-007 | L.5.2.5 | Quality Assurance Surveillance Plan (QASP) — Describe QA processes and metrics tracking | II — Tech | Vol II, Section 5.0 | Compliant | QASP aligned with PWS performance standards | QA Lead | 2026-04-16
L-008 | L.5.3.1 | Management Approach — Organizational chart, staffing plan, and communication strategy | III — Mgmt | Vol III, Section 1.0 | Compliant | Org chart finalized; staffing plan approved | PM | 2026-04-19
L-009 | L.5.3.2 | Key Personnel — Resumes for PM, Deputy PM, Technical Lead; 5-page max per resume | III — Mgmt | Vol III, Section 2.0 | Partial | PM and Tech Lead resumes ready; Deputy PM TBD | HR/Recruiting | 2026-04-21
L-010 | L.5.3.3 | Subcontract Management Plan — Identify major subs; describe oversight and flow-down requirements | III — Mgmt | Vol III, Section 3.0 | Compliant | Teaming agreements executed; flow-downs mapped | Subcontracts Mgr | 2026-04-18
L-011 | L.5.4.1 | Past Performance — 5 relevant contracts within last 5 years; include CPARS ratings and POC info | IV — PP | Vol IV, Section 1.0 | Compliant | 5 references selected; questionnaires sent | BD Lead | 2026-04-17
L-012 | L.5.4.2 | Past Performance Questionnaires — Submit PPQ to each reference; provide completed forms in proposal | IV — PP | Vol IV, Section 2.0 | Partial | 3 of 5 questionnaires returned; following up on 2 | BD Lead | 2026-04-24
L-013 | L.5.5.1 | Cost/Price Volume — Fully loaded labor rates by LCAT; indirect rate build-up; basis of estimate | V — Cost | Vol V, Section 1.0 | Compliant | Rate build-up complete; DCAA-auditable format | Finance Dir | 2026-04-20
L-014 | L.5.5.2 | Subcontractor Pricing — Include sub cost proposals; adequate price competition or cost analysis | V — Cost | Vol V, Section 2.0 | Non-Compliant | Awaiting 2 sub cost proposals; deadline approaching | Subcontracts Mgr | 2026-04-27
L-015 | L.5.6.1 | CDRL Deliverables List — Acknowledge all CDRLs in DD Form 1423; provide delivery schedule | II — Tech | Vol II, Appendix A | Compliant | All 23 CDRLs mapped and acknowledged | Tech Writer | 2026-04-16
L-016 | L.5.6.2 | DD Form 254 — Security Classification Guide acknowledgment; personnel clearance plan | I — Admin | Vol I, Section 3.0 | Compliant | DD 254 reviewed; FSO coordination complete | FSO | 2026-04-17
L-017 | L.5.7.1 | Small Business Subcontracting Plan — Meet or exceed SB goals per FAR 19.704; include ISR/SSR commitment | I — Admin | Vol I, Section 4.0 | Partial | SB plan at 35% vs 38% target; identifying additional SBs | SB Liaison | 2026-04-22
L-018 | L.5.7.2 | Organizational Conflict of Interest (OCI) — Mitigation plan per FAR 9.5; disclose potential conflicts | I — Admin | Vol I, Section 5.0 | N/A | No OCIs identified; self-certification letter prepared | Legal | 2026-04-16
L-019 | L.5.8.1 | Section 508 Compliance — Describe approach to accessible deliverables per Section 508 of Rehab Act | II — Tech | Vol II, Section 6.0 | Compliant | 508 compliance plan based on WCAG 2.1 AA | IT Lead | 2026-04-18
L-020 | L.5.8.2 | Phase-In/Phase-Out Plan — Describe contractor demobilization and data/IP transfer at contract end | II — Tech | Vol II, Section 7.0 | Partial | Phase-out plan outline drafted; detail needed on IP transfer | PM | 2026-04-23
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com
Generated: September 2026 ¦ Updated: FAC 2025-06

## Instructions
RFP Compliance Matrix — Instructions
Purpose
This compliance matrix ensures your proposal response addresses every requirement in the RFP's Section L (Instructions to Offerors). It maps each requirement to your proposal volume, section, and current compliance status. A complete, accurate compliance matrix is the single most important tool for avoiding non-compliance findings during evaluation.
Column Definitions
Req #: A unique identifier for tracking each requirement (e.g., L-001, L-002). Use a consistent numbering scheme that maps to the RFP section structure.
Section L Reference: The specific paragraph or section number from the RFP's Section L where this requirement appears (e.g., L.5.2.1).
Requirement Summary: A concise restatement of the requirement in your own words. Include page limits, format restrictions, and key deliverables specified.
Volume: The proposal volume where this requirement will be addressed (e.g., Volume I — Administrative, Volume II — Technical, Volume III — Management, Volume IV — Past Performance, Volume V — Cost/Price).
Page/Section in Proposal: The exact section and page reference in your proposal where this requirement is addressed. Update as the proposal develops.
Response Status: Current compliance status: Compliant (fully addresses the requirement), Partial (partially addresses; gaps remain), Non-Compliant (does not yet address the requirement), N/A (not applicable to your offer).
Compliance Note: Brief explanation of your compliance approach or identification of gaps. For Partial/Non-Compliant items, describe what is needed to achieve compliance.
Owner: The individual responsible for drafting or completing the response to this requirement.
Due Date: The internal deadline for completing the response to this requirement. Set dates well before the proposal submission deadline.
Tips for Avoiding Non-Compliance
1. Start Early: Begin the compliance matrix as soon as the RFP is released. Do not wait for the proposal outline to be complete.
2. Read Section M: Cross-reference Section M (Evaluation Criteria) with Section L. Evaluators score based on M; your proposal must respond to L in a way that maximizes M scores.
3. Use Shredding: Perform a detailed 'RFP shred' — break every sentence in Section L into individual requirements. A single paragraph may contain 3-5 discrete requirements.
4. Track Amendments: Update the matrix whenever an RFP amendment is issued. Amendments frequently change requirements, page limits, or evaluation criteria.
5. Color Review: Conduct color reviews (Pink/Red/Gold) using this matrix as the checklist. Every row should be 'Compliant' before Gold review.
6. Cross-Reference CDRLs: Ensure all Contract Data Requirements List (CDRL) items in Section J are addressed in your technical volume.
7. Compliance = Responsiveness: A non-compliant proposal may be rated 'unacceptable' and eliminated from competition regardless of technical merit. Compliance is non-negotiable.
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com
License & Use
This template is licensed for use on one program, by one organization, under your Acqlerate purchase. Customize the text, branding, and layout freely for your own program. Deploying it company-wide, sharing it outside your organization, or reselling it requires an Acqlerate Team License (acqlerate.com/team).