## RACI Matrix
RACI Matrix — DoD Program Stakeholders
R=Responsible ¦ A=Accountable ¦ C=Consulted ¦ I=Informed
Legend: | R | Responsible — Does the work | A | Accountable — Approves/owns the outcome | C | Consulted — Provides input before decision | I | Informed — Notified after decision
Activity / Decision | PM | PEO | CO | COR | DCMA | DCAA | Contr PM | Sys Engr | Finance | Legal
Program Initiation | R | A | C | I | I |  | I | C | C | C
Requirements Development | R | A | I | C | I |  | C | R | I | I
Acquisition Strategy | R | A | C | I | I | C | I | C | C | C
Source Selection Planning | C | A | R | C | I |  | I | C | I | C
RFP Development & Release | C | I | R | C |  |  |  | C | I | C
Proposal Evaluation | R | I | A | C |  |  |  | R | C | C
Contract Award | I | A | R | I | I |  | I |  | C | C
Kickoff Meeting | R | I | C | R | I |  | R | C | I
Monthly IPR / Status Review | R | I | I | A | I |  | R | C | C
Quarterly Program Review | R | A | I | C | C |  | R | C | C
EVM / CPR Review | R | I | I | C | C | C | R |  | R
CDR / PDR Review | R | A | I | C | C |  | R | R | I
Test Planning | C | I | I | C | C |  | R | R | I
Test Execution | I | I | I | R | C |  | R | R | I
Deliverable Acceptance | I | I | I | R | C |  | R | C | I
Invoice Review & Approval | I | I | A | R | C | C | R |  | R
Contract Modification | R | A | R | C | I | I | C | C | C | C
Risk Review Board | R | I | I | C | I |  | R | C | C
COR Surveillance | I | I | I | R | C |  | I
CPARS Rating | C | I | A | R | C |  | I
Nunn-McCurdy Reporting | R | A | I | I | I |  | C | C | R | C
APB Baseline Update | R | A | I | I | I |  | C | C | R
Milestone Decision Review | R | A | C | I | C |  | C | R | C | C
Contract Close-Out | C | I | R | R | C | C | R |  | R | C
Lessons Learned / AAR | R | I | I | C | I |  | R | C | I
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com

## Instructions
RACI Matrix — Instructions
Purpose
The RACI matrix clarifies roles and responsibilities across DoD program activities. It prevents confusion about who makes decisions, who needs to be consulted, and who should be kept informed. A well-maintained RACI matrix is essential for effective program governance.
RACI Definitions
R — Responsible: The person or role that performs the work. Multiple people can be Responsible for the same activity, but ensure clarity about who does what.
A — Accountable: The single person who approves or has final authority for the activity's outcome. There MUST be exactly one 'A' per row. This is typically the most senior decision authority for that activity.
C — Consulted: People whose input is sought before a decision or action. This is two-way communication — they provide expertise, review, or concurrence.
I — Informed: People who are notified after a decision is made or action is completed. This is one-way communication — they need to know, but their input is not required.
Stakeholder Roles
PM: Government Program Manager — Overall program execution authority, responsible to PEO for cost, schedule, and performance.
PEO: Program Executive Officer / DASA — Senior acquisition authority; provides oversight, milestone decisions, and resource allocation.
CO: Contracting Officer — Legal authority to obligate government funds, award/modify contracts, and make contractual determinations.
COR: Contracting Officer's Representative — The CO's eyes and ears on the program; monitors contractor performance and technical deliverables.
DCMA: Defense Contract Management Agency — Government contract administration, including EVMS surveillance, property administration, and delivery acceptance.
DCAA: Defense Contract Audit Agency — Audits contractor accounting systems, incurred costs, and forward pricing rate proposals.
Contractor PM: Contractor's Program Manager — Leads the contractor team; responsible for executing the contract's technical, schedule, and cost requirements.
Systems Engineer: Government or contractor lead systems engineer — Technical authority for design, architecture, and systems integration decisions.
Finance: Finance / Comptroller — Manages program budget execution, obligation plans, and financial reporting.
Legal: Legal Counsel — Provides legal advice on contract matters, protests, disputes, intellectual property, and regulatory compliance.
How to Customize
1. Review each activity row and adjust the RACI assignments to match your program's specific governance structure and delegation of authority.
2. Add or remove activities as needed for your program type (ACAT I vs. ACAT III, services vs. systems).
3. Ensure every row has exactly one 'A' — accountability must be unambiguous.
4. Brief all stakeholders on the RACI matrix at the kickoff meeting and include it in the Program Management Plan.
5. Update the RACI matrix whenever organizational changes occur or new stakeholders join the program.
Template by Acqlerate — Defense Acquisitions Academy ¦ www.acqlerate.com