## Instructions
Burn Rate Tracker — How to Use This
What this is for:
A month-by-month tracker for how fast you're spending against your funded ceiling — so you catch
an overrun (or an underrun that puts your next option year at risk) while there's still time to act,
not at the program review where you find out the hard way.
How to use it:
1. Go to the "Burn Rate Tracker" tab.
2. Fill in the blue cells at the top: program name, contract number, Total Obligated Amount (TOA),
and your period of performance start/end dates.
3. Each month, enter that month's ACTUAL spend in the blue "Actual Monthly Spend" column. Everything
else — cumulative totals, variance, projected exhaustion date, status flag — recalculates on its own.
4. Check the Dashboard section at the top. If Status shows "AT RISK", you have a real conversation to
have with your cost analyst or Contracting Officer before the next status report, not after.
Color legend:
Blue text = your inputs. Edit these.
Black text = formulas. Don't overwrite these or the sheet stops recalculating correctly.
Yellow fill = key assumptions that drive the whole sheet (TOA, PoP dates).
Built for a 12-month performance period (a base year or a single option year). If your period runs
longer, copy the last month's row formulas down and extend the Month/Date columns to match.
This is a planning and early-warning tool, not your official cost report. It doesn't replace your
contract's EVM reporting, your cost analyst's numbers, or a certified Incurred Cost Submission.
Reconcile it against your actual accounting system data — this is only as accurate as what you type in.

## Burn Rate Tracker
Burn Rate Tracker
Program / Contract Name | Example: Fleet Sustainment Support Services |  | DASHBOARD
Contract / Task Order # | N00019-25-F-0142 |  | Months of Actuals Entered | 5
Total Obligated Amount (TOA) | 2400000 |  | Spent to Date | 1059000
Period of Performance — Start | 2026-01-01 |  | Remaining Funds | 1341000
Period of Performance — End | 2026-12-31 |  | % of TOA Spent | 44.12%
Months in Period | 12 |  | Current Monthly Burn Rate (3-mo avg) | 221333.3333
Straight-Line Monthly Plan | 200000 |  | Projected Months to Exhaustion | 6.0587
|  |  | Status | ON TRACK
Month # | Month | Planned Cumulative $ | Actual Monthly Spend | Actual Cumulative $ | Variance ($, Actual − Planned) | Variance (%) | Remaining Funds ($)
1 | 2026-01-01 | 200000 | 185000 | 185000 | -15000 | -7.5% | 2215000
2 | 2026-02-01 | 400000 | 210000 | 395000 | -5000 | -1.25% | 2005000
3 | 2026-03-01 | 600000 | 198000 | 593000 | -7000 | -1.167% | 1807000
4 | 2026-04-01 | 800000 | 240000 | 833000 | 33000 | 4.125% | 1567000
5 | 2026-05-01 | 1000000 | 226000 | 1059000 | 59000 | 5.9% | 1341000
6 | 2026-06-01 | 1200000 |  | 1059000 | -141000 | -11.75% | 1341000
7 | 2026-07-01 | 1400000 |  | 1059000 | -341000 | -24.36% | 1341000
8 | 2026-08-01 | 1600000 |  | 1059000 | -541000 | -33.81% | 1341000
9 | 2026-09-01 | 1800000 |  | 1059000 | -741000 | -41.17% | 1341000
10 | 2026-10-01 | 2000000 |  | 1059000 | -941000 | -47.05% | 1341000
11 | 2026-11-01 | 2200000 |  | 1059000 | -1141000 | -51.86% | 1341000
12 | 2026-12-01 | 2400000 |  | 1059000 | -1341000 | -55.88% | 1341000
13 |  |  |  | 1059000 |  |  | 1341000
14 |  |  |  | 1059000 |  |  | 1341000
15 |  |  |  | 1059000 |  |  | 1341000
16 |  |  |  | 1059000 |  |  | 1341000
17 |  |  |  | 1059000 |  |  | 1341000
18 |  |  |  | 1059000 |  |  | 1341000
19 |  |  |  | 1059000 |  |  | 1341000
20 |  |  |  | 1059000 |  |  | 1341000
21 |  |  |  | 1059000 |  |  | 1341000
22 |  |  |  | 1059000 |  |  | 1341000
23 |  |  |  | 1059000 |  |  | 1341000
24 |  |  |  | 1059000 |  |  | 1341000
Formulas:
Month = IF([Month #]<=B8,EDATE(B6,[Month #]-1),"")