## Instructions
Acqlerate
DoD Acquisition Training · acqlerate.com
Cost & Burn Rate Tracker — How to Use This
What this is:
A working cost model for a contractor PM: enter your negotiated rates once, log labor, ODCs, and
travel as they happen, and the Dashboard tab builds up your fully burdened cost, applies G&A and fee,
and tracks it against your funded ceiling month by month — the same buildup your finance team runs,
just visible to you instead of buried in a system you don't have access to.
Tab order — fill these in first, in this order:
1. Rates — your negotiated Fringe, Overhead, G&A, and Fee rates. Everything else depends on these.
2. FundingMods — log your original award and every funding modification since. This is what sets
your current TOA (Total Obligated Amount) — it is NOT a single static number anymore, it's the
running total of your funding log, which is how it actually works on a real contract.
3. Dashboard — enter Program Name, Contract #, and Period of Performance dates near the top.
4. Personnel — one row per person on the program: Employee #, name, LCAT, Exempt or Non-Exempt,
salary (exempt) or hourly rate (non-exempt), standard annual hours (2080 is the usual default),
start/end date, and PTO accrual rate. This is the roster the Labor tab looks people up from —
set it up before you start logging hours.
Then, log costs as they happen:
5. Labor — one row per person, per month. Type the Employee # and the Month #; name, LCAT, and
both hourly rates fill in automatically from Personnel. You only type Regular Hours, OT Hours
(non-exempt only), and PTO Hours. Fringe, OH, and Fully Burdened $ calculate automatically.
Permissible Hours prorates each person's standard capacity for the month — full for a normal
month, partial if they started or left mid-month — so Hours Variance shows over/under at a
glance. OT pays at 1.5x straight time and only applies to Non-Exempt people. PTO Balance on the
Personnel tab updates automatically as you log PTO Hours here.
6. ODCs — log each purchase as a line item (date, category, description, month #, amount). The
Monthly Rollup section at the bottom totals them automatically by month.
7. Travel — same idea as ODCs: log each trip/expense as a line item, it rolls up by month.
The Dashboard tab does the rest automatically:
Labor + ODCs + Travel → Subtotal → + G&A → Total Cost → + Fee → Total Billed for the month. That
rolls into cumulative spend, variance against your straight-line plan, a 3-month rolling burn rate,
a projected fund-exhaustion date, and a plain-language status flag.
One thing to know about "Planned Cumulative $":
It's a simple straight-line split of your TOA across the months in your period (TOA ÷ months). It
does NOT itself apply your rates. So if your spend is more labor-heavy some months and more ODC/
travel-heavy in others, or your burdened rate is high, your actual Total Billed will naturally run
above or below that flat line even when you're executing exactly to your real program plan. Use the
variance and burn rate as a trend to watch, not a hard pass/fail on any single month.
Color legend:
Blue text = your inputs. Edit these.
Green text = formulas that pull from another tab.
Black text = formulas within the same tab. Don't overwrite these.
Yellow fill = key assumptions that drive the whole workbook (rates, TOA inputs).
A note on Permissible Hours and PTO:
Permissible Hours is a simple day-in-month proration of a person's standard annual hours ÷ 12 —
it's an approximation for spotting under/over-recorded time at a glance, not a payroll-grade
calendar. PTO Accrued YTD is just accrual rate × months with logged hours; it doesn't model accrual
caps, waiting periods, or your company's specific PTO policy. Treat both as early-warning signals —
your actual timekeeping and HR systems are always the system of record.
This is a planning and early-warning tool, not your official cost report.
It doesn't replace your contract's EVM reporting, your cost analyst's numbers, or a certified
Incurred Cost Submission. Reconcile it against your actual accounting system — this is only as
accurate as what you type in. And double-check your fee base and G&A base against your own
company's DCAA-approved rate structure — the defaults here are common conventions, not universal ones.

## Rates
| Negotiated Rates | Acqlerate · acqlerate.com
Fringe Rate (%) | 35% | Applied to Direct Labor. Covers benefits (health, retirement, PTO).
Overhead (OH) Rate (%) | 55% | Applied to (Direct Labor + Fringe). Covers indirect labor, facilities, and fringe on indirect staff. Base varies by company — check your DCAA-approved rate agreement.
G&A Rate (%) | 12% | Applied to Total Cost Input (fully burdened labor + ODCs + Travel). Covers company-wide G&A: executive, finance, HR, business development.
Fee Type in Use | Fixed | Type exactly "Fixed" or "Award" (case-sensitive) to switch which fee rate below is used.
Fixed Fee Rate (%) | 7% | Used if Fee Type = "Fixed". A flat % of Total Cost that doesn't vary with performance (CPFF).
Target Award Fee Rate (%) | 10% | Used if Fee Type = "Award". This is the MAX pool rate — actual earned fee depends on your award fee score (see the CPAF lesson). This tracker assumes 100% earned for planning; adjust down if you have a current-period score.
Applicable Fee Rate (auto) | 7% | Picked automatically from the Fee Type cell above. This is what the Dashboard tab actually uses.
Fee base note: |  | This tracker applies fee to Total Cost (burdened labor + ODCs + Travel + G&A). Some contracts exclude ODCs, travel, or facilities capital cost of money from the fee base — check your specific contract's fee clause (FAR 52.216 series) before relying on this for real billing.

## FundingMods
| Funding Modification Log |  |  | Acqlerate · acqlerate.com
Mod # | Date | Description | Funding Added / (Removed) $ | Cumulative TOA $
P00000 (Award) | 2026-01-01 | Original award — base period | 2000000 | 2000000
P00001 | 2026-05-01 | Incremental funding — added scope | 400000 | 2400000
Current TOA (auto) | 2400000 | The cumulative total as of the last modification entered above.
Acqlerate · DoD Acquisition Training · acqlerate.com

## Dashboard
| Cost & Burn Rate Dashboard | [12 empty] | Acqlerate · acqlerate.com
Program / Contract Name |  | Example: Fleet Sustainment Support Services
Contract / Task Order # |  | N00019-25-F-0142
Period of Performance — Start |  | 2026-01-01
Period of Performance — End |  | 2026-12-31
Months in Period |  | 12
Current TOA (from FundingMods tab) |  | 2400000
Straight-Line Monthly Plan |  | 200000
SUMMARY
Months of Actuals Entered |  | 12
Spent to Date |  | 158475.5767
Remaining Funds |  | 2241524.4233
% of TOA Spent |  | 6.603%
Current Monthly Burn Rate (3-mo avg) |  | 0
Projected Months to Exhaustion |  | —
Status |  | AT RISK — UNDERRUNNING (option year risk)
Month # | Month | Planned Cumulative $ | Labor $ | ODCs $ | Travel $ | Subtotal (L+O+T) | G&A $ | Total Cost | Fee $ | Total Billed (This Month) | Actual Cumulative $ | Variance $ | Variance % | Remaining Funds $
1 | 2026-01-01 | 200000 | 40118.1444 | 14200 | 1090 | 55408.1444 | 6648.9773 | 62057.1217 | 4343.9985 | 66401.1202 | 66401.1202 | -133598.8798 | -66.8% | 2333598.8798
2 | 2026-02-01 | 400000 | 28771.3217 | 3100 | 0 | 31871.3217 | 3824.5586 | 35695.8803 | 2498.7116 | 38194.5919 | 104595.7122 | -295404.2878 | -73.85% | 2295404.2878
3 | 2026-03-01 | 600000 | 0 | 0 | 1150 | 1150 | 138 | 1288 | 90.16 | 1378.16 | 105973.8722 | -494026.1278 | -82.34% | 2294026.1278
4 | 2026-04-01 | 800000 | 0 | 8600 | 0 | 8600 | 1032 | 9632 | 674.24 | 10306.24 | 116280.1122 | -683719.8878 | -85.46% | 2283719.8878
5 | 2026-05-01 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116280.1122 | -883719.8878 | -88.37% | 2283719.8878
6 | 2026-06-01 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116280.1122 | -1083719.8878 | -90.31% | 2283719.8878
7 | 2026-07-01 | 1400000 | 9054.0865 | 0 | 0 | 9054.0865 | 1086.4904 | 10140.5769 | 709.8404 | 10850.4173 | 127130.5295 | -1272869.4705 | -90.92% | 2272869.4705
8 | 2026-08-01 | 1600000 | 26155.747 | 0 | 0 | 26155.747 | 3138.6896 | 29294.4366 | 2050.6106 | 31345.0472 | 158475.5767 | -1441524.4233 | -90.1% | 2241524.4233
9 | 2026-09-01 | 1800000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158475.5767 | -1641524.4233 | -91.2% | 2241524.4233
10 | 2026-10-01 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158475.5767 | -1841524.4233 | -92.08% | 2241524.4233
11 | 2026-11-01 | 2200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158475.5767 | -2041524.4233 | -92.8% | 2241524.4233
12 | 2026-12-01 | 2400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158475.5767 | -2241524.4233 | -93.4% | 2241524.4233
Acqlerate · DoD Acquisition Training · acqlerate.com
Formulas:
Month = EDATE(C5,[Month #]-1)

## Personnel
| Personnel | [14 empty] | Acqlerate · acqlerate.com
One row per person. Enter Employee Type as exactly "Exempt" (salaried) or "Non-Exempt" (hourly, OT-eligible).
Employee # | Employee Name | LCAT | Employee Type | Annual Salary (Exempt only) | Direct Hourly Rate (Non-Exempt only) | Standard Annual Hours | Straight-Time Rate $/hr | OT Rate $/hr (1.5x) | Start Date | End Date (optional) | PTO Accrual (hrs/mo) | PTO Beginning Balance (hrs) | Months Worked YTD | PTO Accrued YTD | PTO Used YTD | PTO Balance (hrs)
123456 | John Smith | Engineer 4 | Exempt | 150000 |  | 2080 | 72.1154 | N/A | 2026-07-10 |  | 8 | 0 | 2 | 16 | 0 | 16
123457 | Maria Alvarez | Program Manager | Exempt | 165000 |  | 2080 | 79.3269 | N/A | 2026-01-01 |  | 8 | 12 | 2 | 16 | 8 | 20
123458 | Dave Chen | Admin Support | Non-Exempt |  | 28.5 | 2080 | 28.5 | 42.75 | 2026-01-01 |  | 6.67 | 5 | 1 | 6.67 | 0 | 11.67
2080
2080
2080
2080
2080
2080
2080
2080
2080
2080
2080
2080
Acqlerate · DoD Acquisition Training · acqlerate.com

## Labor
| Labor | [16 empty] | Acqlerate · acqlerate.com
Itemized Timesheet Log — one row per person, per month worked
Employee # | Employee Name | LCAT | Month # | Month | Regular Hours | OT Hours | PTO Hours | Permissible Hours | Hours Variance | Straight Rate $/hr | OT Rate $/hr | Regular $ | OT $ | PTO $ | Direct Labor $ | Fringe $ | OH $ | Fully Burdened Labor $
123456 | John Smith | Engineer 4 | 7 | 2026-07-01 | 60 | 0 | 0 | 123.0108 | -63.0108 | 72.1154 | N/A | 4326.9231 | 0 | 0 | 4326.9231 | 1514.4231 | 3212.7404 | 9054.0865
123456 | John Smith | Engineer 4 | 8 | 2026-08-01 | 173.33 | 0 | 0 | 173.3333 | -0.0033333 | 72.1154 | N/A | 12499.7596 | 0 | 0 | 12499.7596 | 4374.9159 | 9281.0715 | 26155.747
123457 | Maria Alvarez | Program Manager | 1 | 2026-01-01 | 173.33 | 0 | 8 | 173.3333 | 7.9967 | 79.3269 | N/A | 13749.7356 | 0 | 634.6154 | 14384.351 | 5034.5228 | 10680.3806 | 30099.2544
123457 | Maria Alvarez | Program Manager | 2 | 2026-02-01 | 173.33 | 0 | 0 | 173.3333 | -0.0033333 | 79.3269 | N/A | 13749.7356 | 0 | 0 | 13749.7356 | 4812.4075 | 10209.1787 | 28771.3217
123458 | Dave Chen | Admin Support | 1 | 2026-01-01 | 150 | 12 | 0 | 173.3333 | -11.3333 | 28.5 | 42.75 | 4275 | 513 | 0 | 4788 | 1675.8 | 3555.09 | 10018.89
Monthly Rollup (auto)
Month # | Month | Total Fully Burdened Labor $
1 | 2026-01-01 | 40118.1444
2 | 2026-02-01 | 28771.3217
3 | 2026-03-01 | 0
4 | 2026-04-01 | 0
5 | 2026-05-01 | 0
6 | 2026-06-01 | 0
7 | 2026-07-01 | 9054.0865
8 | 2026-08-01 | 26155.747
9 | 2026-09-01 | 0
10 | 2026-10-01 | 0
11 | 2026-11-01 | 0
12 | 2026-12-01 | 0
Acqlerate · DoD Acquisition Training · acqlerate.com
Formulas:
Month = IF([Month #]="","",EDATE(Dashboard!$C5,[Month #]-1))
Employee Name = EDATE(Dashboard!$C5,[Employee #]-1)

## ODCs
| ODCs |  |  | Acqlerate · acqlerate.com
Itemized Log
Date | Category | Description | Month # | Amount $
2026-01-14 | Materials | Replacement network switches (5) | 1 | 14200
2026-02-03 | Equipment | Test bench calibration | 2 | 3100
2026-04-20 | Materials | Spare parts kit | 4 | 8600
| LOG TOTAL |  |  | 25900
Monthly Rollup (auto)
Month # | Month | Total ODCs $
1 | 2026-01-01 | 14200
2 | 2026-02-01 | 3100
3 | 2026-03-01 | 0
4 | 2026-04-01 | 8600
5 | 2026-05-01 | 0
6 | 2026-06-01 | 0
7 | 2026-07-01 | 0
8 | 2026-08-01 | 0
9 | 2026-09-01 | 0
10 | 2026-10-01 | 0
11 | 2026-11-01 | 0
12 | 2026-12-01 | 0
Acqlerate · DoD Acquisition Training · acqlerate.com
Formulas:
Category = EDATE(Dashboard!$C5,[Date]-1)

## Travel
| Travel |  |  | Acqlerate · acqlerate.com
Itemized Log
Date | Category | Description | Month # | Amount $
2026-01-20 | Airfare | PM — kickoff meeting, NAS Norfolk | 1 | 480
2026-01-20 | Lodging | PM — kickoff meeting, 3 nights | 1 | 610
2026-03-10 | Airfare + Per Diem | Lead Engineer — site visit | 3 | 1150
| LOG TOTAL |  |  | 2240
Monthly Rollup (auto)
Month # | Month | Total Travel $
1 | 2026-01-01 | 1090
2 | 2026-02-01 | 0
3 | 2026-03-01 | 1150
4 | 2026-04-01 | 0
5 | 2026-05-01 | 0
6 | 2026-06-01 | 0
7 | 2026-07-01 | 0
8 | 2026-08-01 | 0
9 | 2026-09-01 | 0
10 | 2026-10-01 | 0
11 | 2026-11-01 | 0
12 | 2026-12-01 | 0
Acqlerate · DoD Acquisition Training · acqlerate.com
Formulas:
Category = EDATE(Dashboard!$C5,[Date]-1)